## 数字小分队待办事项
项目 | 进展跟踪记录 | 优先级 | 需求人 | 负责人 | 配合人/部门 | 交付日期 | 状态 | 备注
hmiphy
sdc release |  | medium | pd | wuchen |  | 2019-07-30 | open
hmiphy syn | need discussion | high | pd | wuchen |  | 2019-07-25 | open
rtl update in //ip/gmi_phy/ | macro behavior .v location | medium | soc dv | wuchen/yangfei |  | 2019-08-15 | open
hmiphy dv coverage report and waiver file | 76% line cov | high | soc dv | yangfei |  | 2019-07-19 | closed
add new test case for D2N7 HMIPHY testing |  | low | liangyan | yangfei |  | 2019-07-30 | open
check HMIPHY Rx clock glitch affect when going to PQ1 state | need check from PCS level | high | soc dv | yangfei |  | 2019-07-30 | open
D2N7 & MKPN7
rtc sdc | wuchen will hold a meeting for RTC sdc review | medium | ck | wangqing |  | ND | open
rtc syn |  | low | ck | wangqing |  | ND | open
rtc soc dv testcase analysis | 29 testcase, 22 finished | medium | ck | wangqing |  | ND | open
rtc code analysis & verification | left some issue from last review on 0702 | medium | ck | wangqing |  | 2019-07-15 | open
5 cell lec related cgpll | gate level netlist needs modification gate level netlist update on 2019-07-22 | high | wengen | wuchen/depeng |  | 2019-07-15 | open
1 cell lec releted systempll | gate level netlist needs modification | high | wengen | wuchen/depeng |  | 2019-07-15 | open
system_pll .v for PD | need delete define related code | medium | wengen | depeng |  | 2019-07-30 | open
system_pll sdc for PD | 5 sdc needed | medium | wengen | depeng |  | 2019-07-30 | open
upf file system_pll for PD | level shifter + top | medium | wengen | depeng |  | 2019-07-30 | open
systempll testview auto generation script | no response for DFT emily, ask verilog environment from DFT | high | wengen | depeng |  | 2019-07-15 | closed
pathfinder
测试文档 |  | medium | Liyuan | wuchen |  | 2019-07-30 | open
ccd
测试文档 |  | low | Yilu | wuchen | ccd | 2019-07-30 | open
IP uvm buildup |  | low | wuchen | team member |  | 2019-12-30 | open
Jtag interface auto gen script | BC1500 wrapper | low | wuchen | depeng |  | 2019-09-30 | open
testview verilog envrionment setiup |  | low | ck | depeng | sam | 2019-12-30 | open
时间跨度比较大的放jira

## 会议需要讨论的内容
07/23 会议讨论目标 | 状态
RTC report， RTC soc verification testcase | done， need check 2 item
RTC logic part schedule | done， 0.1 version schedule
hmiphy syn issue | later internal meeting

## RTC task & status
序号 | 里程碑/任务描述 | 进展跟踪记录 | 负责人 | 配合人/部门 | 计划开始时间 | 计划完成时间 | 优先级 | 状态
1 | GF14LPP_PRTC Circuit Integration and Analysis |  | Yongjiang |  | 2019-07-01 | 2019-07-31 |  | On-going
1.1 | GF14LPP_PRTC schematic spice in and circuit integration |  | Yongjiang |  | 2019-07-03 | 2019-07-10 |  | On-going
1.2 | GF14LPP_ARTC & GF4LPP_PRTC integration |  | Yongjiang |  | 2019-07-11 | 2019-07-12
1.3 | GF14LPP_PRTC function block and circuit principle analysis at GF14 |  | Yongjiang | wangqing | 2019-07-15 | 2019-07-31
1.4 | PRTC & ARTC analyze report at GF14 |  | Yongjiang | wangqing | 2019-08-01 | 2019-08-06
2 | PRTC Simulation and Interface at N7 |  | Yongjiang |  | 2019-08-01 | 2020-01-20
2.1 | PRTC porting to N7 |  | Yongjiang | Zhongjian | 2019-08-01 | 2019-08-05
2.2 | PRTC macro design and simulation N7 |  | Yongjiang |  | 2019-08-05 | 2019-09-15
2.3 | PRTC floor plan |  | Yongjiang |  | 2019-09-15 | 2019-09-20
2.4 | PRTC pre-sim report |  | Yongjiang |  | 2019-09-20 | 2019-09-30
2.5 | PRTC layout |  | Zhongjian |  | 2019-09-20 | 2019-11-10 | primary verison
2.6 | PRTC post-sim |  | Yongjiang |  | 2019-10-10 | 2019-12-30 | GDS fix
2.7 | PRTC post-sim report |  | Yongjiang |  |  | 2020-01-20
2.8 | PRTC view generate |  | Yongjiang |  |  | 2020-01-15
3 | ARTC Custom macros Simulation at N7 |  |  |  | 2019-08-01 | 2019-10-25
3.1 | ARTC custiom macros（pass_gate,, outgate) porting to N7 |  |  | Zhongjian | 2019-08-01 | 2019-08-05
3.2 | ARTC custom macros design and simulation at N7 |  |  |  | 2019-08-06 | 2019-08-31
3.3 | ARTC custiom macros floor plan |  |  |  | 2019-09-01 | 2019-09-06
3.4 | ARTC custom macros pre-sim report |  |  |  | 2019-09-07 | 2019-09-20
3.5 | ARTC custiom macros layout |  |  |  | 2019-09-06 | 2019-09-30
3.6 | ARTC custom macros post-sim |  |  |  | 2019-09-25 | 2019-10-15
3.7 | ARTC custom macros post-sim report |  |  |  | 2019-10-15 | 2019-10-25
4 | ARTC RTC macro at N7 |  | wuchen |  | 2019-06-01 | 2019-09-30
4.1 | RTC Code analyze, verification,SDC |  | wangqing |  | 2019-07-01 | 2019-08-20
4.2 | RTC stand cell |  | zhangwei |  | 2019-08-01 | 2019-08-31
4.3 | RTC Syn and release |  | zhangwei |  | 2019-08-01 | 2019-08-31
4.4 | RTC dft netlist |  | ccd |  | 2019-08-24 | 2019-08-31
4.5 | RTC macro PD |  | pd |  | 2019-08-15 | 2019-09-30
4.6 | RTC verification with PD netlist |  | wangqing |  | 2019-09-22 | 2019-09-30
5 | ARTC SRAM macro at N7 |  | Yaoqishuang |  | 2019-08-01 | 2019-10-30
5.1 | SRAM integrate at GF14
5.2
5.3
5.4 | SRAM layout |  |  |  |  | 2019-10-15
5.5
6 | ARTC bits macro at N7 |  | wuchen |  | 2019-08-01 | 2019-10-30
6.1
6.2
6.3
6.4 | GDS fix |  |  |  |  | 2019-10-15
6.5
7 | ARTC Prescaler macro at N7 |  | wuchen |  | 2019-08-01 | 2019-10-30
7.1
7.2
7.3
7.4 | GDS fix |  |  |  |  | 2019-10-15
7.5
8 | ARTC layout integrate and ESD check |  | Zhongjian |  | 2019-10-15 | 2019-11-15
8.1 | ARTC layout integrate
8.2 | ESD check
9 | PRTC & ARTC co-sim and generate views |  | Yongjiang | wangqing | 2019-10-01 | 2020-01-15
9.1 | function view sim & DV check
9.2 | pre_cosim
9.3 | post_cosim
9.4 | create views |  |  |  | 2019-11-15 | 2020-01-15

## ARTC APR Part Schedule
序号 | 里程碑/任务描述 | 事项 | 进展跟踪记录 | 负责人 | 配合人/部门 | 计划开始时间 | 计划完成时间 | 状态 | 备注
1 | Spec, Architectural and Floorplan |  |  |  |  | 2019-07-23 | 2019-07-31
1.1 | Spec |  |  |  |  | 2019-07-23 | 2019-08-06 | closed
1.2 | Architecture |  |  |  |  | 2019-07-23 | 2019-07-31 | closed
1.3 | Floor-plan guideline |  |  | yongjiang | wangqing | 2019-07-23 | 2019-07-31 | open
3 | Verification |  |  |  |  | 2019-07-23 | 2019-08-13
3.1 | testchip environment |  |  |  |  | 2019-07-23 | 2019-08-06 | open
3.2 | Check list |  |  |  |  | 2019-07-23 | 2019-08-06 | open
3.3 | Debug |  |  |  |  | 2019-07-23 | 2019-08-13 | open
4 | DE & DV phase sign off |  |  |  |  | 2019-08-13 | 2019-08-20
4.1 | Lint/CDC （/0in /VC_RDC/VC_CDC check 待定） |  |  |  |  | 2019-08-13 | 2019-08-20 | open
4.2 | Testing Method check & testing pattern deliver |  |  |  |  | 2019-08-13 | 2019-08-20 | open
4.3 | SDC merge & deliver |  |  |  |  | 2019-08-01 | 2019-08-20 | open
5 | Synthesis |  |  |  |  | 2019-08-01 | 2019-08-31
5.1 | Synthesis flow analysis |  |  |  |  | 2019-08-01 | 2019-08-08 | open
5.2 | 0.1 version netlist release |  |  |  |  | 2019-08-08 | 2019-08-15 | open
5.3 | Formal check flow building |  |  |  |  | 2019-08-15 | 2019-08-22 | open
5.4 | 1.0 version netlist release |  |  |  |  | 2019-08-01 | 2019-08-24 | open
6 | DFT |  |  |  |  | 2019-08-24 | 2019-08-31
6.1 | Scan sdc generation |  |  |  |  | 2019-08-24 | 2019-08-31 | open
7 | Syn & DFT phase sign off |  |  |  |  | 2019-08-24 | 2019-08-31
7.1 | Formal check |  |  |  |  | 2019-08-24 | 2019-08-31 | open
7.2 | SDC review |  |  |  |  | 2019-08-24 | 2019-08-31 | open
7.3 | syn report clean |  |  |  |  | 2019-08-24 | 2019-08-31 | open
8 | Physical Design |  |  |  |  | 2019-08-15 | 2019-09-30
8.1 | PR |  |  |  |  | 2019-08-15 | 2019-09-30 | open
8.2 | 1.0 version PV/timing/power clean |  |  |  |  | 2019-08-15 | 2019-09-22 | open
9 | Back annoation simulation |  |  |  |  | 2019-09-22 | 2019-09-29
9.1 | check list |  |  |  |  | 2019-09-22 | 2019-09-25 | open
9.2 | simuation & debug |  |  |  |  | 2019-09-22 | 2019-09-29 | open
10 | signoff |  |  |  |  | 2019-09-22 | 2019-09-30
10.1 | PR result check |  |  |  |  | 2019-09-22 | 2019-09-30 | open
Formulas:
计划开始时间 = [计划开始时间, row above]
计划开始时间 = [计划完成时间, row above]
计划完成时间 = [计划开始时间]+14
计划完成时间 = [计划完成时间, row above]

## AI
会议纪要：7/23
序号 | 问题描述及状态跟踪 | 状态 | 备注
1 | 研究一下 BIOS RAM 和 CMOS （ 供电，生成形式） | open
2 | wrclk 和 1hz的关系， istop会不会在1hz 沿 前后 | open
3 |  | open
4 |  | open
5 |  | open
6 |  | open
7 |  | open
8 |  | open
9 |  | open